| Date | 03-10-2026 |
| --- | --- |
| Team ID | SWTID-2026-8713 |
| Project Name | Implement Client Script & UI Policy (Incident) |
| Maximum Marks | 5 Marks |

## Project Planning Phase

Product Backlog, Sprint Schedule, and Estimation

The following table outlines the product backlog and sprint schedule for implementing Client Scripts and UI Policies on the ServiceNow Incident form so that fields become mandatory, read-only or visible when defined conditions are met.

| Sprint | Functional Req (Epic) | USN | User Story / Task | Point s | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | UI Policy – Mandatory Fields | USN-1 | As a developer, I can create a UI policy that makes Close code and Close notes mandatory when State is Resolved or Closed. | 3 | High | Thabeshwin |
| Sprint-1 | UI Policy – Mandatory Fields | USN-2 | As a developer, I can make Short description mandatory for every new incident. | 2 | High | Thabeshwin |
| Sprint-1 | UI Policy – Visibility and Read-only | USN-3 | As a developer, I can show or hide fields (for example, On hold reason) based on State and Category. | 5 | High | Supriya |
| Sprint-2 | UI Policy – Visibility and Read-only | USN-4 | As a developer, I can make fields read-only for closed incidents. | 1 | Medium | Thabeshwin |
| Sprint-2 | Client Script – onLoad | USN-5 | As a developer, I can write an onLoad Client Script that sets the initial form state and shows guidance. | 2 | High | Supriya |
| Sprint-2 | Client Script – onChange | USN-6 | As a developer, I can write an onChange Client Script on Category, State, Impact or Urgency that updates other fields. | 3 | High | Supriya |
| Sprint-2 | Client Script – onSubmit | USN-7 | As a developer, I can write an onSubmit Client Script that validates the data before save. | 3 | High | Supriya |
| Sprint-2 | Form Guidance | USN-9 | As a service desk agent, I see only the fields that matter for the current State and Category. | 2 | High | Supriya |
| Sprint-2 | Form Guidance | USN- 10 | As an agent, I get a clear message when I enter incorrect or inconsistent data. | 1 | High | Supriya |
| Sprint-3 | Testing and Verification | USN-8 | As a developer, I can test every rule by changing fields on the form and checking the browser console. | 5 | Medium | Sakthivel S |
| Sprint-3 | Rule Maintenance | USN- 11 | As an administrator, I can activate, deactivate and update the Client Scripts and UI Policies. | 3 | Medium | Vishal |

Team members: Vishal (requirements & configuration), Thabeshwin (UI Policy – mandatory and read-only), Supriya (UI Policy – visibility and Client Scripts), Sakthivel S (testing and documentation).

# Project Tracker, Velocity & Burndown Chart

Tracking sprint progression, calculating team velocity, and visual reporting methodology.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 10 Days | 05 Oct 2026 | 16 Oct 2026 | -- | -- |
| Sprint-2 | 12 | 10 Days | 19 Oct 2026 | 30 Oct 2026 | -- | -- |
| Sprint-3 | 8 | 10 Days | 02 Nov 2026 | 13 Nov 2026 | -- | -- |

## Velocity Calculation

Each sprint is planned for 10 working days. The planned workload is 10, 12 and 8 story points for Sprints 1, 2 and 3 (30 points in 30 days).

Average Velocity (AV) = Total Story Points / Total Sprint Days = 30 points / 30 days = 1.0 Story Point per Day

Planned velocity: 30 points / 3 sprints = 10 story points per sprint.

The "Story Points Completed" and "Sprint Release Date (Actual)" columns are filled in as each sprint is closed.

## Burndown Chart

Planned burndown for the three sprints (actual progress is added as stories move to Done)

A burndown chart is a graphical representation of work left to do versus time. In this project the Y-axis shows the outstanding story points (starting at 30) and the X-axis shows the sprint timeline. As stories such as the Mandatory Fields UI Policy (USN-1) or the onSubmit Client Script (USN-7) are moved to "Done", the line drops, giving measurable progress and showing whether the Incident form rules will be delivered on schedule.